## Summary
Takasbank on-prem EDW - ETL tool comparison
ODI, Informatica PowerCenter, dbt, Cloudera Data Platform, Apache Spark ¦ as of 2026-10-14
Recommendation
1. Select Oracle Data Integrator 14c as the enterprise ELT platform: pushdown into the existing Exadata, PL/SQL-friendly, supported to 2030/2033.
2. Serve near-real-time operational ('izleme') reports from the Kale Active Data Guard read-only standby, not from an ETL tool.
3. Use GoldenGate (via ODI JKM) only for data products whose S0 SLA is proven, after the licence question is settled.
4. Keep dbt-core + dbt-oracle as the qualified alternative and procurement-free fallback; run the PoC head-to-head ODI vs dbt.
5. Exclude PowerCenter (fails support-horizon gate; successor needs a cloud control plane). Do not build the core DWH on Cloudera or Spark.
Metric | ODI | PowerCenter | dbt | CDP | Spark
Weighted total (base)
Rank (base)
Knock-out gates
Average use-case fit (1-5)
5-year TCO band
Weighted total (Oracle-team-first)
Weighted total (Real-time-first)
Weighted total (Cost-first)
How to use this workbook
- Yellow cells are inputs: weights on 'Criteria & Weights', scores on 'Scoring Matrix' and 'Use-Case Fit', PoC results on 'PoC Plan'.
- All totals, ranks, gate outcomes and scenario winners are formulas and recalculate on change.
- The tools are not like-for-like (suite vs framework vs platform vs engine); each is scored as a deployable stack with its CDC/orchestration companions.
- Vault note: Obsidian Vault/Kendi Notlarım/ETL Araç Karşılaştırması - Ekim 2026.md. Source of numbers: comparison_data.py.

## Criteria & Weights
Evaluation criteria and weights
Yellow cells are inputs. Base weights drive the Scoring Matrix; scenario weights drive the Sensitivity sheet. Each column must sum to 100.
# | Criterion | What good looks like at Takasbank | Base (Takasbank profile) | Oracle-team-first | Real-time-first | Cost-first
1 | Exadata / Oracle pushdown and performance | Runs set-based work inside Exadata (Smart Scan, HCC, parallel DML), handles 2B-row SWIFT and 20M/day takas volumes without a second compute tier. | 14 | 16 | 10 | 12
2 | Real-time, CDC and operational reporting | Supports S0 near-real-time and S1 micro-batch for izleme screens and intraday Fon Bilgilendirme without touching prod Kale. | 12 | 8 | 24 | 8
3 | Security, on-prem and regulatory compliance | Fully on-prem with no external control plane; BDDK/KVKK/SPK fit; TDE/VPD/redaction respected; security patches through the horizon. | 10 | 10 | 10 | 10
4 | Governance: lineage, metadata, audit, data quality | Column-level source-to-report lineage, run lineage, audit trail and data-quality rules for regulatory reports. | 10 | 8 | 8 | 8
5 | Team skill fit and learning curve | Usable by an Oracle DBA / PL/SQL team with no DWH/ETL background; hiring market in Turkey. | 10 | 16 | 8 | 10
6 | Source connectivity | Kale standby, ARSIV, CekDB, BIST Replica BIDB / Borsa DWH, FTP/CSV, EPIAS web services, possible Postgres/MSSQL. | 8 | 6 | 10 | 6
7 | Transformation and modelling | SCD2, bitemporal core, incremental merge, set-based logic, reuse of existing PL/SQL. | 8 | 8 | 6 | 8
8 | 5-year total cost of ownership | Licence + support + infrastructure + people over five years (higher score = lower cost). | 8 | 8 | 6 | 22
9 | Operations and orchestration | Automic integration, gün sonu event triggering, restart from failure, monitoring, without a 24/7 team. | 7 | 8 | 8 | 6
10 | DevOps: Git, CI/CD, automated tests | Version control, code review, automated tests and promotion DEV -> TEST -> PREPROD -> PROD. | 6 | 6 | 4 | 5
11 | Vendor viability, roadmap and local support | Supported release horizon, roadmap risk, ownership changes, partners in Turkey. | 7 | 6 | 6 | 5
Total (must be 100)

## Scoring Matrix
Weighted scoring matrix (scores 1-5, base weights)
Each tool is scored as a deployable stack incl. required CDC/orchestration companions. Weighted total = SUMPRODUCT(weights, scores) / 5, so 100 = perfect.
Criterion | Weight | ODI | PowerCenter | dbt | CDP | Spark
Exadata / Oracle pushdown and performance |  | 5 | 3 | 5 | 2 | 2
Real-time, CDC and operational reporting |  | 3 | 3 | 2 | 4 | 4
Security, on-prem and regulatory compliance |  | 4 | 2 | 4 | 4 | 2
Governance: lineage, metadata, audit, data quality |  | 4 | 4 | 3 | 4 | 2
Team skill fit and learning curve |  | 4 | 3 | 4 | 1 | 1
Source connectivity |  | 4 | 5 | 1 | 5 | 3
Transformation and modelling |  | 4 | 4 | 4 | 3 | 3
5-year total cost of ownership |  | 3 | 2 | 5 | 1 | 2
Operations and orchestration |  | 4 | 4 | 3 | 2 | 1
DevOps: Git, CI/CD, automated tests |  | 3 | 2 | 5 | 3 | 4
Vendor viability, roadmap and local support |  | 4 | 1 | 2 | 4 | 2
Weighted total (0-100)
Rank
Knock-out gate status (see Gates)
Scoring rationale
Criterion | Weight | ODI | PowerCenter | dbt | CDP | Spark
Exadata / Oracle pushdown and performance | 14 | 5 - E-LT by design: generated SQL runs in the target Exadata; Oracle KMs use external tables, parallel DML, MERGE and partition exchange. | 3 - Engine-based ETL; Pushdown Optimization (extra option) can push to Oracle, but an ETL server tier remains. | 5 - Every model compiles to SQL executed in Exadata; incremental merge and microbatch strategies supported by dbt-oracle. | 2 - Processing happens on the Cloudera cluster; Oracle is reached via JDBC/Sqoop-style pulls and results written back for MSTR. | 2 - Reads and writes Oracle through JDBC; no use of Smart Scan; 2B-row SWIFT reload is the worst case.
Real-time, CDC and operational reporting | 12 | 3 - Batch and micro-batch natively; S0 only via GoldenGate JKM (separate licence, DBA concerns). ADG standby covers raw izleme screens. | 3 - PowerExchange CDC for Oracle (separate licence) gives log-based capture; real-time option exists. | 2 - No CDC or streaming; microbatch runs give S1 at best; S0 must come from ADG or GoldenGate. | 4 - Kafka + Flink + NiFi give true streaming; Oracle CDC still needs Debezium/LogMiner or GoldenGate on Kale side. | 4 - Structured Streaming and 4.x Real-time Mode with Kafka + Debezium; parts still experimental.
Security, on-prem and regulatory compliance | 10 | 4 - Fully on-prem; agents run inside the bank; credentials in the ODI repository/wallet; relies on Oracle DB security (TDE, VPD). | 2 - On-prem today, but security fixes stop after Extended Support (Mar 2027); successor needs an internet-connected Secure Agent and cloud control plane. | 4 - Self-hosted Core sends no data out; runs with DB accounts; secrets handled by the runner. Do not use dbt platform (SaaS). | 4 - On-prem with Kerberos, Ranger, TLS; larger attack surface and second security perimeter. | 2 - Everything (Kerberos/TLS, secrets, authorisation) is self-built and self-patched.
Governance: lineage, metadata, audit, data quality | 10 | 4 - Repository holds mappings, column lineage and impact analysis; run history per session. DQ needs custom checks or Oracle EDQ. | 4 - Metadata Manager lineage and mature audit; DQ via separate Informatica products. | 3 - DAG lineage, docs site and built-in tests; column-level lineage only in the SaaS platform; run artifacts must be harvested. | 4 - Atlas lineage and Ranger audit across the cluster; lineage breaks at the Oracle boundary. | 2 - Lineage via OpenLineage/DIY; no built-in catalogue or audit.
Team skill fit and learning curve | 10 | 4 - SQL-centric; PL/SQL developers become productive quickly. GUI and KM concepts need training. | 3 - No in-house ETL skills; PowerCenter developers available in the Turkish market (MKK). | 4 - SQL first; Jinja macros, YAML and Git are new but small steps for SQL people. | 1 - Hadoop, Kafka, Flink, Spark, Kerberos skills absent; scarce and expensive hires. | 1 - Python/Scala distributed-systems engineering; furthest from the PL/SQL team.
Source connectivity | 8 | 4 - Oracle, JDBC (Postgres/MSSQL), files, FTP, web-service tools; BIDB pull from Borsa DWH as Ondata described. | 5 - Broadest connector catalogue of the five: files, FTP, web services, all RDBMS, mainframe. | 1 - None: dbt only transforms what is already in the database; landing must be built separately. | 5 - NiFi plus Kafka Connect cover files, FTP, web services, APIs and all databases. | 3 - JDBC and files are fine; FTP/web services need custom code.
Transformation and modelling | 8 | 4 - Built-in SCD2 and incremental IKMs; bitemporal patterns via custom KM; existing procedure SQL reusable. | 4 - Rich transformation library, SCD wizards, lookups; logic lives in the engine, not in SQL. | 4 - Snapshots (SCD2), incremental models, tests, macros; bitemporal handled with custom macros. | 3 - Spark SQL / Hive / Iceberg MERGE are capable, but the integrated core would be split between two platforms. | 3 - Unlimited logic, but core tables live in Oracle, so every load is a cross-system write.
5-year total cost of ownership | 8 | 3 - Processor licences on agent hosts plus 22% annual support; HA adds WebLogic/Coherence. No extra compute (Exadata). | 2 - Quote-based licence, extended-support premium, and a forced migration to IDMC within the 5-year window. | 5 - No licence; people cost for building the ingestion/orchestration framework. | 1 - CCU + data-under-management subscription, a new server cluster, and a platform team on top of Exadata. | 2 - No licence, but cluster hardware plus 3-5 platform/data engineers.
Operations and orchestration | 7 | 4 - Load plans with restart, agent HA, Automic triggers scenarios via command line or web service. | 4 - Workflow Manager/Monitor, restart and recovery are mature. | 3 - CLI runs from Automic; `dbt retry` for restarts; monitoring built from run_results artifacts. | 2 - Cloudera Manager helps, but a multi-service cluster needs 24/7 operations Takasbank lacks. | 1 - Scheduler, monitoring, restart and upgrades are all DIY.
DevOps: Git, CI/CD, automated tests | 6 | 3 - VCS/Git integration and deployment archives exist, but branching and merging repository objects is clumsy. | 2 - Repository-centric; XML export for Git; weak CI/CD. | 5 - Best-in-class: Git, pull requests, CI, environment targets, slim CI. | 3 - Code-based jobs are Git-friendly; platform configuration is not. | 4 - Code-first and testable; CI/CD must be assembled.
Vendor viability, roadmap and local support | 7 | 4 - Oracle; 14c supported to 2030/2033; Borsa Istanbul reference; local integrators. | 1 - On-prem product at end of standard support; now part of Salesforce; partner reported no new on-prem sales. | 2 - Open source with no on-prem SLA; Oracle adapter community/Oracle-maintained and not yet on v2 engine; vendor focus is cloud. | 4 - 7.3.2 LTS supported to 2032; established vendor with Turkish banking references. | 2 - Community project; support only via third parties; fast release cadence to track.

## Gates
Knock-out gates (pass / conditional / fail before scoring)
A Fail removes the tool from the shortlist regardless of its weighted score. Conditional = passes only with the stated mitigation.
Gate | Requirement | ODI | PowerCenter | dbt | CDP | Spark
G1 | Runs fully on-prem with no external control plane or internet-connected agent | Pass | Conditional | Pass | Pass | Pass
G2 | Vendor-supported release with security fixes for 5+ years (to late 2031) | Pass | Fail | Conditional | Pass | Conditional
G3 | Production-grade support for Oracle Database 19c/23ai on Exadata | Pass | Pass | Pass | Pass | Pass
Overall
Gate evidence
Gate | Requirement | ODI | PowerCenter | dbt | CDP | Spark
G1 | Runs fully on-prem with no external control plane or internet-connected agent | Pass: All components inside the bank. | Conditional: 10.5 yes; the only supported successor (CDI-PC/IDMC) needs a cloud control plane. | Pass: dbt-core only; dbt platform (SaaS) excluded. | Pass: Cloudera Base on premises. | Pass: Self-managed.
G2 | Vendor-supported release with security fixes for 5+ years (to late 2031) | Pass: 14c Premier to Dec 2030, Extended to Dec 2033. | Fail: Standard support ended Mar 2026; Extended to Mar 2027; Sustaining to 2029 without new fixes. | Conditional: Apache 2.0 with indefinite OSS commitment, but no SLA; each minor line supported 1 year. | Pass: 7.3.2 LTS to Mar 2032. | Conditional: Community maintenance only; third-party support needed.
G3 | Production-grade support for Oracle Database 19c/23ai on Exadata | Pass: Native Oracle KMs, Exadata-aware loading. | Pass: Certified Oracle connectivity. | Pass: dbt-oracle supports on-prem Oracle via python-oracledb. | Pass: JDBC source/target. | Pass: JDBC source/target.

## Sensitivity
Sensitivity: weighted totals under alternative weightings
Totals are live formulas over 'Criteria & Weights' scenario columns and 'Scoring Matrix' scores.
Scenario | ODI | PowerCenter | dbt | CDP | Spark | Winner
Base (Takasbank profile)
Oracle-team-first
Real-time-first
Cost-first
Reading: ODI leads in the base, Oracle-team-first and real-time-first scenarios; dbt overtakes ODI only when TCO is weighted at 22%. PowerCenter's total is irrelevant because it fails gate G2.

## Capability Detail
Tool profiles
Vendor facts verified 2026-10-14; see Sources.
Attribute | Oracle Data Integrator | Informatica PowerCenter | dbt (dbt-core + dbt-oracle) | Cloudera Data Platform (Base on premises) | Apache Spark (self-managed)
Product / version | ODI 14c (14.1.2.0.0) | PowerCenter 10.5.x (final on-prem line) | dbt-core 1.12 + dbt-oracle 1.12 (dbt v2/Fusion has no Oracle adapter yet) | Cloudera Base on premises 7.3.2 LTS + Cloudera Streaming (Kafka, Flink) + Flow Management (NiFi) | Apache Spark 4.2.0 (Jul 2026) on Kubernetes/YARN
Category | ELT suite (pushdown, E-LT) | ETL engine suite | In-warehouse SQL transformation framework | Big-data platform (storage + compute + streaming) | Distributed processing engine
Deployable stack evaluated | ODI 14c agents + Knowledge Modules; GoldenGate JKM only for proven S0/S1 feeds; Automic calls ODI scenarios / load plans | PowerCenter Integration Service + Repository; PowerExchange CDC for Oracle (separate licence); Pushdown Optimization option | dbt-core + dbt-oracle on Linux runners; ingestion by PL/SQL + external tables/SQL*Loader (or ODI); Automic runs `dbt build`; Git + CI | Cloudera Base cluster (Ozone/HDFS, Iceberg, Hive/Impala, Spark), Cloudera Streaming (Kafka/Flink, Kafka Connect + Debezium), NiFi for files/web services, Atlas/Ranger (SDX) | Spark 4.2 (SQL, Structured Streaming, Declarative Pipelines) + Kafka + Debezium + Airflow/Automic + Iceberg or JDBC write-back to Oracle; DIY security and lineage (OpenLineage)
Licensing | Per processor or Named User Plus on every host running an ODI agent (list ref. USD 30k/processor + 22% annual support). WebLogic EE + Coherence EE needed for clustered agent HA. GoldenGate licensed separately on capture/delivery hosts. | Quote-based; on-prem PowerCenter no longer sold to new customers per the Informatica partner (BI Technology) - successor CDI-PC is IPU consumption-based via an internet-connected IDMC Secure Agent. | Apache 2.0, no licence fee. dbt platform (SaaS) is not usable on-prem; no vendor SLA for self-hosted Core. Fivetran + dbt Labs merger completed 1 Jun 2026. | Subscription by Cloudera Compute Units (cores/6 + RAM GB/12) plus Data Under Management since Feb 2025; quote-based. Requires its own commodity-server cluster - cannot run on Exadata. | Apache 2.0, no licence fee. No vendor support unless bought from a third party.
Lifecycle / support | FMW 14.1.2 Premier Support to Dec 2030, Extended to Dec 2033. ODI 12c Premier ends Dec 2026, Extended Dec 2027. Next FMW release targeted 2027. | Standard support ended 31 Mar 2026. Paid Extended Support to 31 Mar 2027, Sustaining Support (no new fixes / security patches) to 31 Mar 2029. Informatica acquired by Salesforce (Nov 2025). | Minor releases roughly quarterly, one year of support each (1.12 critical support to Jul 2027). dbt-oracle maintained by Oracle; v2 parser does not recognise Oracle yet. | 7.3.2 LTS GA Mar 2026, supported to Mar 2032. 7.3.1 EoS Dec 2026, 7.1.9 Oct 2028. | Feature release roughly every 6-7 months (4.0 May 2025, 4.1 Dec 2025, 4.2 Jul 2026); maintenance releases for a limited window per line.
Strengths | - Generates set-based SQL that runs inside Exadata (Smart Scan, HCC, parallel DML, partition exchange) - no second compute tier - Knowledge Modules for SCD2, incremental merge, CDC and bulk load (external tables, SQL*Loader, DB link from standby) - Native GoldenGate journalizing (JKM) when a data product truly needs S0/S1 - Repository-based lineage and impact analysis; load plans with restart from failure point - Already in the Turkish capital-markets ecosystem (Borsa Istanbul uses ODI); local partners exist | - Very broad connectivity (files, FTP, web services, mainframe, all major RDBMS) - Mature workflow manager, restartability and operational monitoring - Metadata Manager lineage; large pool of PowerCenter developers in Turkey (MKK uses it) - Takasbank already has an Informatica relationship (TDM for non-prod masking) | - Pure SQL pushdown on Exadata - same compute advantage as ODI - Code-first: Git, pull-request review, automated tests, environments, docs site - Built-in data tests, snapshots (SCD2), incremental merge and microbatch strategies - Zero licence cost and no procurement - can start the pilot immediately | - Strongest native streaming stack (Kafka, Flink, NiFi) for S0 event pipelines - SDX governance: Atlas lineage, Ranger policies, Kerberos - fully on-prem - NiFi handles FTP/CSV, EPIAS web services and API ingestion well - Scales to data sizes far beyond Takasbank's (~10 TB Kale) | - Most flexible engine: Python/Scala/SQL, ML, streaming (Real-time Mode), CDC APIs in 4.2 - No licence cost; huge community - Code-first, testable, Git-native
Weaknesses | - GUI-centric development; Git integration exists but merge/branching is awkward compared to code-first tools - Licence follows agent hosts; HA topology adds WebLogic/Coherence licences - Real-time capability is borrowed from GoldenGate, which the DBA team distrusts and has no 24/7 cover for - 14c requires Python 3 for custom KMs (Jython deprecated) - small learning item | - End-of-support product: buying it in 2026 for a 10-year DWH is buying a forced migration - Successor (CDI-PC / IDMC) puts the control plane in the cloud - conflicts with 'data and operations stay inside the bank' - Row-by-row engine by default; full pushdown to Exadata needs the PDO option and still leaves an ETL server tier - Repository-based development; weak Git/CI story | - Transformation only: no extraction, file handling, web services or CDC - a landing framework must be built - Model-level lineage only in Core; column-level lineage is a dbt platform (SaaS) feature - No commercial support for on-prem Core; Oracle adapter lags the cloud-warehouse adapters - Jinja/YAML and Git workflow are new to a PL/SQL team | - A second data platform beside three Exadata machines that are 77-90% free - Data must leave Exadata to be processed and come back for MSTR - double copies, double security perimeter - Hadoop/Kafka/Spark skills absent; needs a platform team and 24/7 operations - Oracle CDC still needs a log reader (Debezium LogMiner or GoldenGate) on the Kale side | - Everything around the engine is DIY: scheduling, security, lineage, monitoring, upgrades - Moves data off Exadata through JDBC - the slowest path for a 2-billion-row SWIFT table - Requires Python/Scala data engineers and a platform team Takasbank does not have - Real-time Mode is still marked experimental for parts of the API
Takasbank fit | Best structural fit: Oracle-only estate, Exadata already paid for, PL/SQL team, Kale-centric sources, files and BIDB pulls. | Fails the support-horizon gate. Only defensible as a short-term bridge for an existing PowerCenter estate - which Takasbank does not have. | Strong transformation layer and the fastest start, but needs a separate, home-built ingestion and orchestration layer. | Over-sized for a 10 TB Oracle-centric DWH. Revisit only for a future streaming/AI or unstructured-data mandate. | Weakest fit: maximum engineering load, minimum use of existing Oracle investment.

## Real-time & Latency
Real-time and operational reporting by latency class (S0-S4)
Score 1-5 = how well the tool stack serves the class without touching prod Kale. Recommended pattern is tool-independent.
Class | Meaning | Takasbank example | Recommended pattern | ODI | PowerCenter | dbt | CDP | Spark
S0 | Near real-time (seconds) | Izleme screens, Team Developer current-state queries | Kale ADG read-only standby on sur; GoldenGate -> LND -> ODS_ projection only for products with a proven SLA | 2 | 3 | 1 | 5 | 4
S1 | Intraday micro-batch (5-30 min) | Fon Bilgilendirme 08:00-17:45 with correction files | Watermark/SCN-based micro-batch from the standby into LND, recompute affected funds only | 4 | 4 | 3 | 5 | 4
S2 | Gün sonu (T-1) | BISTECH SPK 13 reports, SWIFT legal reports, takas positions | SCN-consistent extract from standby after the machine-readable gün sonu event | 5 | 4 | 5 | 3 | 3
S3 | Scheduled file / external feed | FTP/CSV, EPIAS web services, Borsa DWH fund contracts, Verda file output | Manifest + checksum landing; external tables for files; web-service pull into LND_FILE / LND_EPIAS | 4 | 5 | 1 | 5 | 3
S4 | Backfill / replay | 10-year fund history, 2013+ SWIFT history, ARSIV yearly rollovers | Replay from immutable landing with a separate load_id; partition exchange for bulk history | 5 | 3 | 5 | 4 | 4
Notes per tool
Class |  |  |  | ODI | PowerCenter | dbt | CDP | Spark
S0 |  |  |  | Only with GoldenGate JKM | PowerExchange CDC / real-time option | Not supported | Kafka/Flink/NiFi native | Structured Streaming + Kafka
S1 |  |  |  | Scheduled load plans, CDC on watermark or GG | Scheduled workflows / CDC | Microbatch incremental, scheduled by Automic | Streaming or micro-batch | Trigger-based micro-batch
S2 |  |  |  | Core use case | Core use case, engine tier | Core use case once landed | Works, but off-Exadata | Works, but off-Exadata
S3 |  |  |  | File and web-service tools | Broadest connectors | Needs separate ingestion | NiFi | Custom code
S4 |  |  |  | Set-based bulk + partition exchange | Engine throughput bound | full-refresh / microbatch backfill | Scales out, then write back | Scales out, then write back

## Use-Case Fit
Fit to Takasbank workloads (1-5)
Workloads taken from the July 2025 DWH presentation and UG meeting notes.
ID | Use case | Volume / behaviour | ODI | PowerCenter | dbt | CDP | Spark
UC1 | SWIFT legal reports | 2B rows / 170 GB since 2013, ~1M messages/day; collapse to ~24M one-row-per-message summary; free-text ID search; T-1. | 5 | 3 | 5 | 3 | 3
UC2 | Fon Bilgilendirme platform | ~60k fund notifications/day, recalculation 08:00-17:45 with correction files; 10-year history via CSV and web service. | 4 | 3 | 3 | 4 | 3
UC3 | Fon islem defterleri | 9M Borsa DWH fund contracts/day (deleted at source after 5 days), cleanse to ~600k, files twice a day per market to Borsa Verda. | 4 | 4 | 2 | 4 | 3
UC4 | BISTECH SPK 13 reports | Kale NOMX + Replica BIDB, after Takas UG gün sonu; replace DB_ARSIV dblink views with PUB snapshots. | 5 | 4 | 4 | 2 | 2
UC5 | EPIAS energy settlement feeds | Order/settlement files via web services, 5-10k records/day, collateral data, avans.takas table. | 3 | 4 | 1 | 5 | 2
UC6 | Operational izleme screens (S0) | Intraday current-state queries now hitting prod Kale from Team Developer / React. | 2 | 2 | 1 | 4 | 3
UC7 | Takas positions and history | ~20M derivative and non-derivative positions/day; yearly banka -> banka_old -> arsiv rollover moves into DWH partitions. | 5 | 3 | 4 | 4 | 4
Average fit

## TCO Drivers
5-year TCO drivers (bands, not quotes)
List prices are public reference points only; Takasbank must obtain quotes. Higher band = higher cost.
Driver | ODI | PowerCenter | dbt | CDP | Spark
Software licence (5 yr) | Medium-High: list ref. USD 30k per processor on agent hosts (x86 core factor 0.5) + 22%/yr support | High: quote-based; extended-support premium; migration to IPU billing within window | None | High: CCU + data-under-management subscription (quote-based) | None
CDC / real-time add-on | GoldenGate per processor on capture/delivery hosts, only for S0 products (licence includes ADG entitlement) | PowerExchange CDC licence | External (ADG / GoldenGate) | Included in Cloudera Streaming subscription; Oracle log reader still needed | Kafka + Debezium (free) - operate yourself
Infrastructure | Low: 2 agent VMs; compute on existing Exadata | Medium: integration-service servers + repository DB | Low: runner VMs; compute on existing Exadata | High: new multi-node cluster (storage, masters, Kafka brokers) | High: new Kubernetes/YARN cluster + Kafka
People (build + run) | 2 data engineers + part-time ODI admin | 2 ETL developers + Informatica admin | 2-3 data engineers (incl. ingestion framework) + DevOps support | Platform team 3-4 + 2 data engineers; 24/7 on-call | 3-5 platform/data engineers; 24/7 on-call
Training / hiring risk | Low-Medium | Medium | Low-Medium | High | High
Exit / migration cost | Medium: logic in KMs/mappings, SQL is visible | High: forced re-platform before 2029 | Low: plain SQL in Git | High | Medium
Overall 5-year band | Medium | High | Low | Very high | High

## Risks
Risk register by tool
Tool | Risk | Likelihood | Impact | Mitigation
ODI | GoldenGate operational burden if S0 products are approved | Medium | High | Serve raw izleme from ADG standby first; GoldenGate only per product with DBA on-call agreed; monitor lag in CTL.
ODI | Licence scope creep (agents on more hosts, HA needs WebLogic EE) | Medium | Medium | Fix agent topology before the PO; standalone agents with Automic-level failover instead of WebLogic cluster.
ODI | GUI development hides logic from code review | Medium | Medium | ODI VCS on Git, naming standards, scenario versioning, generated-SQL review in PR.
PowerCenter | Product end-of-life forces a second migration | High | High | Do not select; if ever considered, price the IDMC migration and confirm on-prem control-plane options in writing.
PowerCenter | Cloud control plane conflicts with data-residency rules | High | High | Legal/compliance review of CDI-PC Secure Agent connectivity before any further evaluation.
dbt | Home-built ingestion framework becomes an unsupported product | Medium | High | Keep landing minimal (external tables, PL/SQL pulls from standby), documented and owned; or pair with ODI for ingestion.
dbt | Oracle adapter lags dbt v2 / Fusion | High | Medium | Pin dbt-core 1.x + dbt-oracle; track adapter roadmap; avoid features exclusive to the SaaS platform.
dbt | No vendor SLA for production incidents | Medium | Medium | Third-party support contract or internal runbooks; failure surface is small because SQL runs in Oracle.
CDP | Second platform without a platform team | High | High | Do not adopt for the core DWH; reconsider only with a funded streaming/AI programme and team.
CDP | Two copies of regulated data and two security perimeters | High | Medium | Ranger/Atlas + KVKK classification on both sides; avoid by keeping the DWH on Exadata.
Spark | DIY platform with no vendor support | High | High | Not recommended; if needed, buy commercial support and limit to non-critical analytics.
Spark | JDBC bottleneck for large Oracle loads | High | Medium | Partitioned parallel reads, or keep heavy SQL inside Exadata.
All | No machine-readable gün sonu completion signal | High | High | Batch-control record (business date, run id, SCN) produced by operations before any S2 pipeline goes live.
All | Historical rows updated in place break incremental loads | Medium | High | Profile change columns on the standby; fall back to SCN snapshots and hash-diff where no reliable timestamp exists.

## PoC Plan
Proof of concept: ODI vs dbt head-to-head on Takasbank data
Run on the Kale standby and DSS, never prod Kale. PowerCenter excluded by gate G2; CDP/Spark excluded by fit.
Test | Name | Use case | What is measured | Acceptance criterion | ODI result | dbt result
T1 | SWIFT bulk + delta | UC1 | Initial load of the 2B-row history and daily delta into the summary table; elapsed time, Exadata CPU/IO, Smart Scan offload ratio. | Daily delta finishes inside the T-1 window; result matches the current Kale query for a sampled set of IDs.
T2 | Intraday Fon recompute | UC2 | Micro-batch from standby every 15 min, with a correction file mid-day. | End-to-end freshness 15 min or better; corrected fund recomputed; reruns are idempotent.
T3 | Borsa contract capture + Verda files | UC3 | Land 9M contracts/day raw; cleanse; produce per-market files twice a day with manifest and hash. | No lost day (5-day source retention); files byte-identical to the current output on a test day.
T4 | SPK report reconciliation | UC4 | Build 3 of the 13 SPK reports from NOMX + Replica BIDB after the gün sonu event. | 100% reconciliation with the current Kale tables for the same business date.
T5 | Replay and backfill | UC7 | Replay a failed day from landing under a new load_id; backfill one year of positions. | Same result as the original run; no manual data fixes.
T6 | Restart after failure | All | Kill a run mid-load. | Restarts from the failed step without duplicates; operator steps documented in a runbook.
T7 | Lineage | UC4 | Trace one SPK report column back to source columns. | Column-level lineage available without manual spreadsheets.
T8 | Automic + gün sonu event | All | Trigger the S2 chain from the batch-control record, not a clock. | Chain starts on the event; failures alert Automic and the owner.
T9 | Security | All | Secrets handling, least-privilege accounts, TDE/VPD/redaction respected, audit of reads/exports. | Security team sign-off; no data or metadata leaves the bank.
T10 | Promotion and CI | All | Promote a change DEV -> TEST -> PREPROD with automated tests. | Repeatable, reviewed deployment with rollback.

## Context & Requirements
Takasbank context that drives the evaluation
Facts from the Obsidian vault notes (meetings, presentations, topology). Not vendor claims.
Topic | Fact
Institution | Post-trade market infrastructure (clearing, CCP, settlement, custody, payments); SPK/BDDK/TCMB regulated; data cannot leave the bank.
Core source | Kale on the kale Exadata: ~90% of all data, ~10 TB, ~7,000 main + ~3,000 backup tables, no ERD; member tables duplicated per schema.
Other sources | ARSIV (banka -> banka_old -> arsiv yearly), CekDB (cheque images as CLOB), BIST Replica BIDB / Borsa DWH, FTP/CSV, EPIAS web services, possibly Postgres/MSSQL.
Hardware | Three Exadata (kale, sur, hisar), ~200 TB each, 77-90% disk free, sur CPU ~6-12%, hisar ~2-3% (Dec 2024 snapshot).
Replicas | Kale has two Data Guard replicas, one on sur; DSS and PREPROD are detached from Kale at 07:00; tvsods is a live copy on kale.
Reporting | Team Developer screens, React web, MicroStrategy (10-20% migrated), member terminal reports, SPK/MASAK/BDDK/Hazine reports with hour-level SLAs.
Real-time demand | 'Izleme' screens are near-real-time current-state views; Fon Bilgilendirme recalculates 08:00-17:45; Piyasalar UG reports performance problems.
Gün sonu | Manually triggered, completion by e-mail; Preprod flashback snapshots 04:00-07:00; no machine-readable completion signal.
Team | IZV: 1 manager + 2 MSTR developers; strong Oracle DBA/PL/SQL; no DWH/ETL experience; table knowledge sits with UG analysts.
Operations | No 24/7 monitoring team; DBA team considers GoldenGate fragile; Automic used as scheduler by several teams.
Licences known | Informatica TDM (masking) only; GoldenGate licence status disputed (Obase: exists; DBA: new); ADG status to be confirmed.
Procurement | Slow; any product needing a new PO delays the pilot.

## Sources
Sources (verified 2026-10-14)
# | Source | URL
1 | Oracle FMW Statement of Direction (14.1.2 support to 2030/2033) | https://blogs.oracle.com/fusionmiddlewaresupport/oracle-fusion-middleware-statement-of-direction-is-now-available
2 | What's new in ODI 14c (14.1.2.0.0) | https://docs.oracle.com/en/middleware/fusion-middleware/data-integrator/14.1.2/odiad/whats-new-oracle-data-integrator.html
3 | Oracle Data Integration products licensing information | https://docs.oracle.com/en/middleware/fusion-middleware/fmwlc/data-integration-products.html
4 | ODI licensing in 2026 (list price reference) | https://redresscompliance.com/oracle-data-integrator-licensing
5 | ODI GoldenGate JKM documentation | https://docs.oracle.com/middleware/odi121301/odi/develop-connectivity-km/ogg.htm
6 | Oracle GoldenGate licensing (includes ADG/XStream entitlement) | https://docs.oracle.com/en/middleware/goldengate/core/21.3/ogglc/oracle-goldengate-licensing-guide.pdf
7 | Informatica community: PowerCenter 10.5.x end of support | https://network.informatica.com/s/question/0D5VM00000m2Kag0AE/informatica-1056
8 | Informatica: PowerCenter EoS does not apply to CDI-PC | https://knowledge.informatica.com/s/article/000245032?language=en_US
9 | CDI-PC April 2026 What's New (mandatory cloud-managed updates) | https://docs.informatica.com/content/dam/source/GUID-1/GUID-1A371312-AE91-482A-ABF1-D612D25A99D6/19/en/CDIPC_April2026_WhatSNew_en.pdf
10 | Salesforce completes acquisition of Informatica (18 Nov 2025) | https://investor.salesforce.com/news/news-details/2025/Salesforce-Completes-Acquisition-of-Informatica/default.aspx
11 | Fivetran + dbt Labs complete merger (1 Jun 2026) | https://www.getdbt.com/blog/fivetran-dbt-labs-complete-merger-to-create-the-data-infrastructure-for-trusted-ai-agents
12 | dbt licensing | https://docs.getdbt.com/docs/dbt-licensing
13 | dbt Fusion adapter availability | https://docs.getdbt.com/docs/fusion/fusion-availability
14 | dbt-oracle releases | https://github.com/oracle/dbt-oracle/releases
15 | dbt Core support lifecycle | https://endoflife.date/dbt-core
16 | Cloudera support lifecycle policy | https://www.cloudera.com/services-and-support/support-lifecycle-policy.html
17 | Cloudera Base on premises 7.3.2 release summary | https://docs.cloudera.com/cdp-private-cloud/latest/release-summaries/index.html
18 | Cloudera licensed metrics (CCU definition) | https://www.cloudera.com/legal/commercial-terms-and-conditions/cloudera-licensed-metrics.html
19 | Apache Spark 4.2.0 release notes | https://spark.apache.org/releases/spark-release-4-2-0.html
20 | Databricks: Introducing Apache Spark 4.1 (Real-time Mode) | https://www.databricks.com/blog/introducing-apache-sparkr-41
21 | Debezium Oracle connector (LogMiner / XStream) | https://debezium.io/documentation/reference/stable/connectors/oracle.html
22 | Oracle GoldenGate Free FAQ (limits) | https://docs.oracle.com/en/middleware/goldengate/free/23/uggfe/frequently-asked-questions.html